## Exporter
Issue Type | Key | Summary | Assignee | Reporter | Priority | Status | Resolution | Created | Updated | Due Date | Comment date | Comment author | Comment | Initial status date | Time in initial status | Time in initial status (s) | Initial status | Final status | Transition date | Transition user | Times | Time in final status | Time in final status (s)
Task | PQVP-77 | As a DevOps Engineer I want to configure AWS monitoring | John Gedeon | Eric Steen | Medium | To Do |  | 3/16/2018, 9:29:16 PM | 3/16/2018, 9:30:34 PM
Task | PQVP-76 | As a developer, I want to implement JMeter to evaluate performance | roberto.obando@qualapps.com | Eric Steen | Medium | To Do |  | 3/16/2018, 9:28:43 PM | 3/16/2018, 9:30:53 PM
Bug | PQVP-75 | Article status reset to submitted when article viewed |  | John Gedeon | Medium | To Do |  | 3/16/2018, 9:26:23 PM | 3/16/2018, 9:31:37 PM
Bug | PQVP-74 | Popular Articles Not Displaying properly | John Gedeon | John Gedeon | Medium | Done | Done | 3/16/2018, 6:59:20 PM | 3/16/2018, 7:46:55 PM |  |  |  |  | 3/16/2018, 6:59:20 PM | 12 seconds | 12 | To Do | In Progress | 3/16/2018, 6:59:32 PM | john.gedeon | 1 | 47 minutes | 2843
[14 empty] | 3/16/2018, 6:59:32 PM | 47 minutes | 2843 | In Progress | Done | 3/16/2018, 7:46:55 PM | john.gedeon | 1 | 3 hours 3 minutes | 10995
Bug | PQVP-73 | Views not incrementing when approved article viewed | John Gedeon | John Gedeon | Medium | Done | Done | 3/16/2018, 6:52:00 PM | 3/16/2018, 7:47:00 PM |  |  |  |  | 3/16/2018, 6:52:00 PM | 6 minutes | 377 | To Do | In Progress | 3/16/2018, 6:58:17 PM | john.gedeon | 1 | 48 minutes | 2923
[14 empty] | 3/16/2018, 6:58:17 PM | 48 minutes | 2923 | In Progress | Done | 3/16/2018, 7:47:00 PM | john.gedeon | 1 | 3 hours 3 minutes | 10990
Bug | PQVP-72 | Login in w/out credentials results in 404 error page | Joe Puli | Eric Steen | Medium | Done | Done | 3/15/2018, 7:56:05 AM | 3/16/2018, 10:44:10 AM |  |  |  |  | 3/15/2018, 7:56:05 AM | 1 days 2 hours 16 minutes | 94578 | To Do | In Progress | 3/16/2018, 10:12:22 AM | eric.steen | 1 | 31 minutes | 1908
[14 empty] | 3/16/2018, 10:12:22 AM | 31 minutes | 1908 | In Progress | Done | 3/16/2018, 10:44:10 AM | admin | 1 | 12 hours 5 minutes | 43559
Story | PQVP-71 | As user I want to make changes to database for new functionality. |  | roberto.obando@qualapps.com | Medium | To Do |  | 3/15/2018, 2:04:16 AM | 3/15/2018, 2:04:22 AM
Story | PQVP-70 | As a dev-ops engineer I want to build the physical database | John Gedeon | Eric Steen | Medium | Done | Done | 3/12/2018, 5:16:16 AM | 3/14/2018, 7:05:08 AM |  |  |  |  | 3/12/2018, 5:16:16 AM | 2 days 1 hours 48 minutes | 179332 | To Do | Done | 3/14/2018, 7:05:08 AM | eric.steen | 1 | 2 days 15 hours 45 minutes | 229502
Story | PQVP-69 | As a technical architect I want to define a logical architecture | Joe Puli | Eric Steen | Medium | Done | Done | 3/12/2018, 5:13:29 AM | 3/14/2018, 7:05:08 AM |  |  |  |  | 3/12/2018, 5:13:29 AM | 2 days 1 hours 51 minutes | 179499 | To Do | Done | 3/14/2018, 7:05:08 AM | eric.steen | 1 | 2 days 15 hours 45 minutes | 229502
Story | PQVP-68 | As a technical architect I want to define the logical and physical architecture | Joe Puli | Eric Steen | Medium | Done | Done | 3/12/2018, 5:13:00 AM | 3/14/2018, 7:05:08 AM |  |  |  |  | 3/12/2018, 5:13:00 AM | 2 days 1 hours 52 minutes | 179527 | To Do | Done | 3/14/2018, 7:05:08 AM | eric.steen | 1 | 2 days 15 hours 45 minutes | 229502
Story | PQVP-67 | As a product manager I want to establish the product backlog to define functional scope | Suresh Kannan | Eric Steen | Medium | Done | Done | 3/12/2018, 4:31:28 AM | 3/12/2018, 4:34:35 AM |  |  |  |  | 3/12/2018, 4:31:28 AM | 18 seconds | 18 | To Do | Done | 3/12/2018, 4:31:46 AM | eric.steen | 1 | 4 days 18 hours 18 minutes | 411503
Story | PQVP-66 | As a technical architect I want to identify all design and run-time tools and frameworks | Joe Puli | Eric Steen | Medium | Done | Done | 3/12/2018, 4:28:59 AM | 3/12/2018, 4:29:34 AM |  |  |  |  | 3/12/2018, 4:28:59 AM | 5 seconds | 5 | To Do | Done | 3/12/2018, 4:29:04 AM | eric.steen | 1 | 4 days 18 hours 21 minutes | 411666
Story | PQVP-65 | As a developer I want to build and configure my local environment | Joe Puli | Eric Steen | Medium | Done | Done | 3/12/2018, 3:53:20 AM | 3/12/2018, 4:34:23 AM |  |  |  |  | 3/12/2018, 3:53:20 AM | 1 minutes | 71 | To Do | Done | 3/12/2018, 3:54:32 AM | eric.steen | 1 | 4 days 18 hours 55 minutes | 413738
Story | PQVP-64 | As a developer I want to build and configure my local environment | Suresh Kannan | Eric Steen | Medium | Done | Done | 3/12/2018, 3:51:46 AM | 3/12/2018, 4:34:10 AM |  |  |  |  | 3/12/2018, 3:51:46 AM | 2 minutes | 166 | To Do | Done | 3/12/2018, 3:54:32 AM | eric.steen | 1 | 4 days 18 hours 55 minutes | 413738
Story | PQVP-63 | As a developer I want to build and configure my local environment | John Gedeon | Eric Steen | Medium | Done | Done | 3/12/2018, 3:50:04 AM | 3/12/2018, 4:33:58 AM |  |  |  |  | 3/12/2018, 3:50:04 AM | 4 minutes | 267 | To Do | Done | 3/12/2018, 3:54:31 AM | eric.steen | 1 | 4 days 18 hours 55 minutes | 413738
Story | PQVP-62 | As a developer I want to create the article rating service |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:43:43 AM | 3/14/2018, 7:06:47 AM
Story | PQVP-61 | As user I want to rate articles. |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:43:43 AM | 3/14/2018, 7:06:46 AM
Story | PQVP-60 | As system I want to capture user views for KA. | roberto.obando@qualapps.com | Eric Steen | Medium | Done | Done | 3/12/2018, 3:43:43 AM | 3/14/2018, 7:05:08 AM |  |  |  |  | 3/12/2018, 3:43:43 AM | 2 days 3 hours 21 minutes | 184885 | To Do | Done | 3/14/2018, 7:05:08 AM | eric.steen | 1 | 2 days 15 hours 45 minutes | 229502
Story | PQVP-59 | As user I want to request updates to KA. |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:43:42 AM | 3/14/2018, 7:06:47 AM
Story | PQVP-58 | As system I want to notify users on KA changes. |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:43:42 AM | 3/14/2018, 7:06:47 AM
Story | PQVP-57 | As system I want to maintain version history. |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:43:42 AM | 3/14/2018, 7:06:47 AM
Story | PQVP-56 | As system I want to capture when created KA. | Joe Puli | Eric Steen | Medium | Done | Done | 3/12/2018, 3:43:42 AM | 3/14/2018, 7:05:08 AM |  |  |  |  | 3/12/2018, 3:43:42 AM | 2 days 3 hours 21 minutes | 184886 | To Do | Done | 3/14/2018, 7:05:08 AM | eric.steen | 1 | 2 days 15 hours 45 minutes | 229501
Story | PQVP-55 | As system I want to capture who created KA. | John Gedeon | Eric Steen | Medium | Done | Done | 3/12/2018, 3:43:42 AM | 3/14/2018, 7:05:08 AM |  |  |  |  | 3/12/2018, 3:43:42 AM | 2 days 3 hours 21 minutes | 184886 | To Do | Done | 3/14/2018, 7:05:08 AM | eric.steen | 1 | 2 days 15 hours 45 minutes | 229501
Story | PQVP-54 | As user I wan to categorize KA to apply to different channels. | John Gedeon | Eric Steen | Medium | Done | Done | 3/12/2018, 3:43:42 AM | 3/14/2018, 7:05:08 AM |  |  |  |  | 3/12/2018, 3:43:42 AM | 2 days 3 hours 21 minutes | 184886 | To Do | Done | 3/14/2018, 7:05:08 AM | eric.steen | 1 | 2 days 15 hours 45 minutes | 229502
Story | PQVP-53 | As a developer I want to create the article search service | roberto.obando@qualapps.com | Eric Steen | Medium | Done | Done | 3/12/2018, 3:43:42 AM | 3/14/2018, 7:05:19 AM |  |  |  |  | 3/12/2018, 3:43:42 AM | 1 hours 13 minutes | 4411 | To Do | In Progress | 3/12/2018, 4:57:12 AM | eric.steen | 1 | 2 days 2 hours 8 minutes | 180487
[14 empty] | 3/12/2018, 4:57:12 AM | 2 days 2 hours 8 minutes | 180487 | In Progress | Done | 3/14/2018, 7:05:19 AM | eric.steen | 1 | 2 days 15 hours 44 minutes | 229490
Story | PQVP-52 | As a developer I want to create the service to manage the article workflow | roberto.obando@qualapps.com | Eric Steen | Medium | Done | Done | 3/12/2018, 3:43:42 AM | 3/14/2018, 7:05:19 AM |  |  |  |  | 3/12/2018, 3:43:42 AM | 1 hours 13 minutes | 4410 | To Do | In Progress | 3/12/2018, 4:57:12 AM | eric.steen | 1 | 2 days 2 hours 8 minutes | 180487
[14 empty] | 3/12/2018, 4:57:12 AM | 2 days 2 hours 8 minutes | 180487 | In Progress | Done | 3/14/2018, 7:05:19 AM | eric.steen | 1 | 2 days 15 hours 44 minutes | 229491
Story | PQVP-51 | As a developer I want to create the service to support article management (CRUD) | roberto.obando@qualapps.com | Eric Steen | Medium | Done | Done | 3/12/2018, 3:43:42 AM | 3/14/2018, 7:05:19 AM |  |  |  |  | 3/12/2018, 3:43:42 AM | 1 hours 13 minutes | 4410 | To Do | In Progress | 3/12/2018, 4:57:12 AM | eric.steen | 1 | 2 days 2 hours 8 minutes | 180487
[14 empty] | 3/12/2018, 4:57:12 AM | 2 days 2 hours 8 minutes | 180487 | In Progress | Done | 3/14/2018, 7:05:19 AM | eric.steen | 1 | 2 days 15 hours 44 minutes | 229491
Story | PQVP-50 | As a Ui developer I want to create the page to search articles | John Gedeon | Eric Steen | Medium | Done | Done | 3/12/2018, 3:43:41 AM | 3/14/2018, 7:05:18 AM |  |  |  |  | 3/12/2018, 3:43:41 AM | 1 hours 13 minutes | 4410 | To Do | In Progress | 3/12/2018, 4:57:12 AM | eric.steen | 1 | 2 days 2 hours 8 minutes | 180487
[14 empty] | 3/12/2018, 4:57:12 AM | 2 days 2 hours 8 minutes | 180487 | In Progress | Done | 3/14/2018, 7:05:18 AM | eric.steen | 1 | 2 days 15 hours 44 minutes | 229491
Story | PQVP-49 | AS a UI developer I want to create the page to manage articles (Create, Read, Update and Delete) | roberto.obando@qualapps.com | Eric Steen | Medium | Done | Done | 3/12/2018, 3:43:41 AM | 3/14/2018, 7:05:19 AM |  |  |  |  | 3/12/2018, 3:43:41 AM | 1 hours 13 minutes | 4411 | To Do | In Progress | 3/12/2018, 4:57:12 AM | eric.steen | 1 | 2 days 2 hours 8 minutes | 180487
[14 empty] | 3/12/2018, 4:57:12 AM | 2 days 2 hours 8 minutes | 180487 | In Progress | Done | 3/14/2018, 7:05:19 AM | eric.steen | 1 | 2 days 15 hours 44 minutes | 229490
Story | PQVP-48 | AS a UI developer I want to create the landing page | Joe Puli | Eric Steen | Medium | Done | Done | 3/12/2018, 3:43:41 AM | 3/14/2018, 7:05:19 AM |  |  |  |  | 3/12/2018, 3:43:41 AM | 1 hours 13 minutes | 4411 | To Do | In Progress | 3/12/2018, 4:57:12 AM | eric.steen | 1 | 2 days 2 hours 8 minutes | 180487
[14 empty] | 3/12/2018, 4:57:12 AM | 2 days 2 hours 8 minutes | 180487 | In Progress | Done | 3/14/2018, 7:05:19 AM | eric.steen | 1 | 2 days 15 hours 44 minutes | 229491
Story | PQVP-47 | As user I want to save KA as favorites. |  | Eric Steen | Medium | Done | Done | 3/12/2018, 3:43:41 AM | 3/16/2018, 9:42:18 PM |  |  |  |  | 3/12/2018, 3:43:41 AM | 1 hours 13 minutes | 4411 | To Do | In Progress | 3/12/2018, 4:57:12 AM | eric.steen | 1 | 4 days 16 hours 45 minutes | 405906
[14 empty] | 3/12/2018, 4:57:12 AM | 4 days 16 hours 45 minutes | 405906 | In Progress | Done | 3/16/2018, 9:42:18 PM | qualapps.jira.read | 1 | 1 hours 7 minutes | 4072
Story | PQVP-46 | As user I want to search for KA in specific categories. | roberto.obando@qualapps.com | Eric Steen | Medium | Done | Done | 3/12/2018, 3:43:41 AM | 3/14/2018, 7:05:19 AM |  |  |  |  | 3/12/2018, 3:43:41 AM | 1 hours 13 minutes | 4411 | To Do | In Progress | 3/12/2018, 4:57:12 AM | eric.steen | 1 | 2 days 2 hours 8 minutes | 180487
[14 empty] | 3/12/2018, 4:57:12 AM | 2 days 2 hours 8 minutes | 180487 | In Progress | Done | 3/14/2018, 7:05:19 AM | eric.steen | 1 | 2 days 15 hours 44 minutes | 229491
Story | PQVP-45 | As user I want to search for KA in all categories. | John Gedeon | Eric Steen | Medium | Done | Done | 3/12/2018, 3:43:41 AM | 3/14/2018, 7:05:19 AM |  |  |  |  | 3/12/2018, 3:43:41 AM | 1 hours 13 minutes | 4412 | To Do | In Progress | 3/12/2018, 4:57:12 AM | eric.steen | 1 | 2 days 2 hours 8 minutes | 180487
[14 empty] | 3/12/2018, 4:57:12 AM | 2 days 2 hours 8 minutes | 180487 | In Progress | Done | 3/14/2018, 7:05:19 AM | eric.steen | 1 | 2 days 15 hours 44 minutes | 229490
Story | PQVP-44 | As system I should not allow duplicate KA creation. | John Gedeon | Eric Steen | Medium | Done | Done | 3/12/2018, 3:43:41 AM | 3/14/2018, 7:05:19 AM |  |  |  |  | 3/12/2018, 3:43:41 AM | 1 hours 13 minutes | 4412 | To Do | In Progress | 3/12/2018, 4:57:12 AM | eric.steen | 1 | 2 days 2 hours 8 minutes | 180487
[14 empty] | 3/12/2018, 4:57:12 AM | 2 days 2 hours 8 minutes | 180487 | In Progress | Done | 3/14/2018, 7:05:19 AM | eric.steen | 1 | 2 days 15 hours 44 minutes | 229490
Story | PQVP-43 | As user I want to archive content. |  | Eric Steen | Medium | In Progress |  | 3/12/2018, 3:43:40 AM | 3/14/2018, 7:06:47 AM |  |  |  |  | 3/12/2018, 3:43:40 AM | 1 hours 13 minutes | 4412 | To Do | In Progress | 3/12/2018, 4:57:12 AM | eric.steen | 1 | 4 days 17 hours 52 minutes | 409977
Story | PQVP-42 | As user I want to publish content. |  | Eric Steen | Medium | Done | Done | 3/12/2018, 3:43:40 AM | 3/16/2018, 9:59:00 PM |  |  |  |  | 3/12/2018, 3:43:40 AM | 1 hours 13 minutes | 4412 | To Do | In Progress | 3/12/2018, 4:57:12 AM | eric.steen | 1 | 4 days 17 hours 1 minutes | 406908
[14 empty] | 3/12/2018, 4:57:12 AM | 4 days 17 hours 1 minutes | 406908 | In Progress | Done | 3/16/2018, 9:59:00 PM | eric.steen | 1 | 51 minutes | 3070
Story | PQVP-41 | As and admin I want to approve content. | John Gedeon | Eric Steen | Medium | In Progress |  | 3/12/2018, 3:43:40 AM | 3/16/2018, 9:59:24 PM |  |  |  |  | 3/12/2018, 3:43:40 AM | 1 hours 13 minutes | 4412 | To Do | In Progress | 3/12/2018, 4:57:12 AM | eric.steen | 1 | 4 days 17 hours 52 minutes | 409978
Story | PQVP-40 | As user I want to categorize articles for different users(managers/juniors/exec). | roberto.obando@qualapps.com | Eric Steen | Medium | Done | Done | 3/12/2018, 3:43:40 AM | 3/14/2018, 7:05:18 AM |  |  |  |  | 3/12/2018, 3:43:40 AM | 1 hours 13 minutes | 4412 | To Do | In Progress | 3/12/2018, 4:57:12 AM | eric.steen | 1 | 2 days 2 hours 8 minutes | 180487
[14 empty] | 3/12/2018, 4:57:12 AM | 2 days 2 hours 8 minutes | 180487 | In Progress | Done | 3/14/2018, 7:05:19 AM | eric.steen | 1 | 2 days 15 hours 44 minutes | 229491
Story | PQVP-39 | As user I want to create articles with rich media. | John Gedeon | Eric Steen | Medium | Done | Done | 3/12/2018, 3:43:40 AM | 3/14/2018, 7:05:19 AM |  |  |  |  | 3/12/2018, 3:43:40 AM | 1 hours 13 minutes | 4412 | To Do | In Progress | 3/12/2018, 4:57:12 AM | eric.steen | 1 | 2 days 2 hours 8 minutes | 180487
[14 empty] | 3/12/2018, 4:57:12 AM | 2 days 2 hours 8 minutes | 180487 | In Progress | Done | 3/14/2018, 7:05:19 AM | eric.steen | 1 | 2 days 15 hours 44 minutes | 229491
Story | PQVP-38 | As user I want to visually mark information sections that apply to certain users(managers/junior staff/exec etc) | John Gedeon | Eric Steen | Medium | Done | Done | 3/12/2018, 3:43:40 AM | 3/14/2018, 7:05:19 AM |  |  |  |  | 3/12/2018, 3:43:40 AM | 1 hours 13 minutes | 4413 | To Do | In Progress | 3/12/2018, 4:57:12 AM | eric.steen | 1 | 2 days 2 hours 8 minutes | 180487
[14 empty] | 3/12/2018, 4:57:12 AM | 2 days 2 hours 8 minutes | 180487 | In Progress | Done | 3/14/2018, 7:05:19 AM | eric.steen | 1 | 2 days 15 hours 44 minutes | 229491
Story | PQVP-37 | As user I want to categorize KA as technical or non technical. | Suresh Kannan | Eric Steen | Medium | Done | Done | 3/12/2018, 3:43:40 AM | 3/14/2018, 7:05:19 AM |  |  |  |  | 3/12/2018, 3:43:40 AM | 1 hours 13 minutes | 4413 | To Do | In Progress | 3/12/2018, 4:57:12 AM | eric.steen | 1 | 2 days 2 hours 8 minutes | 180487
[14 empty] | 3/12/2018, 4:57:12 AM | 2 days 2 hours 8 minutes | 180487 | In Progress | Done | 3/14/2018, 7:05:19 AM | eric.steen | 1 | 2 days 15 hours 44 minutes | 229491
Story | PQVP-36 | As user I want to create knowledge. | John Gedeon | Eric Steen | Medium | Done | Done | 3/12/2018, 3:43:39 AM | 3/14/2018, 6:58:19 AM |  |  |  |  | 3/12/2018, 3:43:39 AM | 1 hours 13 minutes | 4392 | To Do | In Progress | 3/12/2018, 4:56:51 AM | eric.steen | 1 | 2 days 2 hours 1 minutes | 180088
[14 empty] | 3/12/2018, 4:56:51 AM | 2 days 2 hours 1 minutes | 180088 | In Progress | Done | 3/14/2018, 6:58:19 AM | eric.steen | 1 | 2 days 15 hours 51 minutes | 229910
Story | PQVP-35 | As user I want to save articles as favorites. |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:36:04 AM | 3/14/2018, 7:06:47 AM
Story | PQVP-34 | As user I want to see the most popular articles. |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:36:04 AM | 3/14/2018, 7:06:48 AM
Story | PQVP-33 | As user I want to see most recent articles |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:36:04 AM | 3/14/2018, 7:06:47 AM
Story | PQVP-32 | As system I want to prevent duplicate article creation. |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:36:03 AM | 3/14/2018, 7:06:47 AM
Story | PQVP-31 | As system I want to capture article views. |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:36:03 AM | 3/14/2018, 7:06:47 AM
Story | PQVP-30 | As user I want to rate article. |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:36:03 AM | 3/14/2018, 7:06:47 AM
Story | PQVP-29 | As user I want to seek update of existing articles. |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:36:03 AM | 3/14/2018, 7:06:47 AM
Story | PQVP-28 | As user I want to be notified upon article life cycle events(submission, approval,update and archival). |  | Eric Steen | Medium | Done | Done | 3/12/2018, 3:36:03 AM | 3/15/2018, 5:28:27 AM |  |  |  |  | 3/12/2018, 3:36:03 AM | 3 days 1 hours 52 minutes | 265920 | To Do | In Progress | 3/15/2018, 5:28:03 AM | admin | 1 | 24 seconds | 24
[14 empty] | 3/15/2018, 5:28:03 AM | 24 seconds | 24 | In Progress | Done | 3/15/2018, 5:28:27 AM | admin | 1 | 1 days 17 hours 21 minutes | 148903
Story | PQVP-27 | As a system I want to capture article life cycle management articles. |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:36:03 AM | 3/14/2018, 7:06:47 AM
Story | PQVP-26 | As user I want to categoriz/channelize and tag knowledge articles. |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:36:03 AM | 3/14/2018, 7:06:47 AM
Story | PQVP-25 | As user I want to create articles with role/group based acesss. |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:36:02 AM | 3/14/2018, 7:06:47 AM
Story | PQVP-24 | As user I want to create articles with attachements. |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:36:02 AM | 3/14/2018, 7:06:47 AM
Story | PQVP-23 | As user I want to create articles with rich text |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:36:02 AM | 3/14/2018, 7:06:47 AM
Story | PQVP-22 | As a Developer I want to build the User Account Service |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:36:02 AM | 3/14/2018, 7:06:47 AM
Story | PQVP-21 | As a Developer I want to build the KA Category data service |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:36:02 AM | 3/14/2018, 7:06:47 AM
Story | PQVP-20 | As a Developer I want to build the KA Search Service |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:36:02 AM | 3/14/2018, 7:06:47 AM
Story | PQVP-19 | As a Developer I want to build the KA WorkFLow Service |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:36:01 AM | 3/14/2018, 7:06:47 AM
Story | PQVP-18 | As a Developer I want to build the KA data service |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:36:01 AM | 3/14/2018, 7:06:47 AM
Story | PQVP-17 | As a UX developer I want to create the search page |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:36:01 AM | 3/14/2018, 7:06:47 AM
Story | PQVP-16 | As a UX developer I want to create the page to create new KA |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:36:01 AM | 3/14/2018, 7:06:47 AM
Story | PQVP-15 | As a UX developer I want to create the page to display "My Approved List" |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:36:01 AM | 3/14/2018, 7:06:47 AM
Story | PQVP-14 | As a UX developer I want to create the page to Manage Categories |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:36:01 AM | 3/14/2018, 7:06:47 AM
Story | PQVP-13 | As a UX developer I want to create the landing page |  | Eric Steen | Medium | Done | Done | 3/12/2018, 3:36:00 AM | 3/16/2018, 9:59:06 PM |  |  |  |  | 3/12/2018, 3:36:00 AM | 2 days 6 hours 59 minutes | 197990 | To Do | In Progress | 3/14/2018, 10:35:51 AM | john.gedeon | 1 | 2 days 11 hours 23 minutes | 213795
[14 empty] | 3/14/2018, 10:35:51 AM | 2 days 11 hours 23 minutes | 213795 | In Progress | Done | 3/16/2018, 9:59:06 PM | eric.steen | 1 | 51 minutes | 3064
Story | PQVP-12 | As a UX developer I want to create the page to display the selected KA to be approved/rejected |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:36:00 AM | 3/14/2018, 7:06:47 AM
Story | PQVP-11 | As a UX developer I want to create the UI Admin Dashboard showing the list of Kas awaiting for approval |  | Eric Steen | Medium | To Do |  | 3/12/2018, 3:35:59 AM | 3/14/2018, 7:06:47 AM
Story | PQVP-9 | As a user I want to create an account/profile . |  | Eric Steen | Medium | Done | Done | 3/8/2018, 5:54:31 AM | 3/16/2018, 9:43:33 PM |  |  |  |  | 3/8/2018, 5:54:31 AM | 3 days 21 hours 24 minutes | 336252 | To Do | Done | 3/12/2018, 3:18:43 AM | eric.steen | 1 | 35 seconds | 35
[14 empty] | 3/12/2018, 3:18:43 AM | 35 seconds | 35 | Done | In Progress | 3/12/2018, 3:19:18 AM | eric.steen | 1 | 4 days 13 hours 10 minutes | 393048
[14 empty] | 3/12/2018, 3:19:18 AM | 4 days 13 hours 10 minutes | 393048 | In Progress | To Do | 3/16/2018, 4:30:07 PM | eric.steen | 1 | 4 seconds | 4
[14 empty] | 3/16/2018, 4:30:07 PM | 4 seconds | 4 | To Do | In Progress | 3/16/2018, 4:30:10 PM | eric.steen | 1 | 5 hours 13 minutes | 18802
[14 empty] | 3/16/2018, 4:30:10 PM | 5 hours 13 minutes | 18802 | In Progress | Done | 3/16/2018, 9:43:33 PM | qualapps.jira.read | 1 | 1 hours 6 minutes | 3997
Story | PQVP-8 | As a user I want to log in. |  | Eric Steen | Medium | Done | Done | 3/8/2018, 5:54:06 AM | 3/16/2018, 9:59:09 PM |  |  |  |  | 3/8/2018, 5:54:06 AM | 3 days 21 hours 24 minutes | 336276 | To Do | Done | 3/12/2018, 3:18:42 AM | eric.steen | 1 | 35 seconds | 35
[14 empty] | 3/12/2018, 3:18:42 AM | 35 seconds | 35 | Done | In Progress | 3/12/2018, 3:19:17 AM | eric.steen | 1 | 4 days 18 hours 39 minutes | 412792
[14 empty] | 3/12/2018, 3:19:17 AM | 4 days 18 hours 39 minutes | 412792 | In Progress | Done | 3/16/2018, 9:59:09 PM | eric.steen | 1 | 51 minutes | 3060
Epic | PQVP-7 | As a system prototype I want to provide Knowledge Development |  | Eric Steen | Medium | To Do |  | 3/8/2018, 5:50:44 AM | 3/8/2018, 5:50:44 AM
Epic | PQVP-6 | As a user I should be able to share my knowledge. |  | Eric Steen | Medium | To Do |  | 3/8/2018, 5:50:24 AM | 3/8/2018, 5:50:24 AM
Epic | PQVP-5 | As a user I should be able to share my knowledge. |  | Eric Steen | Medium | To Do |  | 3/8/2018, 5:49:49 AM | 3/8/2018, 5:49:49 AM
Epic | PQVP-4 | As a user I wan to create Knowledge Articles (KAS) |  | Eric Steen | Medium | To Do |  | 3/8/2018, 5:49:03 AM | 3/8/2018, 5:49:03 AM
Story | PQVP-3 | As a dev-ops engineer I want to configure the Test/Production environment | John Gedeon | Eric Steen | Medium | Done | Done | 3/8/2018, 5:48:46 AM | 3/12/2018, 4:33:47 AM |  |  |  |  | 3/8/2018, 5:48:46 AM | 3 days 21 hours 29 minutes | 336595 | To Do | Done | 3/12/2018, 3:18:40 AM | eric.steen | 1 | 35 seconds | 35
[14 empty] | 3/12/2018, 3:18:40 AM | 35 seconds | 35 | Done | In Progress | 3/12/2018, 3:19:16 AM | eric.steen | 1 | 36 minutes | 2165
[14 empty] | 3/12/2018, 3:19:16 AM | 36 minutes | 2165 | In Progress | Done | 3/12/2018, 3:55:21 AM | eric.steen | 1 | 4 days 18 hours 54 minutes | 413689
Story | PQVP-2 | As a dev-ops engineer I want to build and configure the CI/CD environment | John Gedeon | Eric Steen | Medium | Done | Done | 3/8/2018, 5:48:40 AM | 3/12/2018, 4:33:28 AM |  |  |  |  | 3/8/2018, 5:48:40 AM | 3 days 21 hours 29 minutes | 336599 | To Do | Done | 3/12/2018, 3:18:39 AM | eric.steen | 1 | 36 seconds | 36
[14 empty] | 3/12/2018, 3:18:39 AM | 36 seconds | 36 | Done | In Progress | 3/12/2018, 3:19:14 AM | eric.steen | 1 | 36 minutes | 2181
[14 empty] | 3/12/2018, 3:19:14 AM | 36 minutes | 2181 | In Progress | Done | 3/12/2018, 3:55:35 AM | eric.steen | 1 | 4 days 18 hours 54 minutes | 413674
Story | PQVP-1 | As a developer I want to build and configure my local environment | roberto.obando@qualapps.com | Eric Steen | Medium | Done | Done | 3/8/2018, 5:48:21 AM | 3/12/2018, 4:32:24 AM |  |  |  |  | 3/8/2018, 5:48:21 AM | 3 days 21 hours 30 minutes | 336616 | To Do | Done | 3/12/2018, 3:18:37 AM | eric.steen | 1 | 36 seconds | 36
[14 empty] | 3/12/2018, 3:18:37 AM | 36 seconds | 36 | Done | In Progress | 3/12/2018, 3:19:13 AM | eric.steen | 1 | 29 minutes | 1748
[14 empty] | 3/12/2018, 3:19:13 AM | 29 minutes | 1748 | In Progress | Done | 3/12/2018, 3:48:21 AM | eric.steen | 1 | 40 seconds | 40
[14 empty] | 3/12/2018, 3:48:21 AM | 40 seconds | 40 | Done | To Do | 3/12/2018, 3:49:01 AM | eric.steen | 1 | 3 seconds | 3
[14 empty] | 3/12/2018, 3:49:01 AM | 3 seconds | 3 | To Do | Done | 3/12/2018, 3:49:04 AM | eric.steen | 2 | 4 days 19 hours 1 minutes | 414066